## Introduction
Carbon Management Toolkit
Introduction: This toolkit’s provides templates and guidance to support project teams in the implemention of effective carbon management practices throughout every stage of a buildings life-cycle. The toolkit includes the following:
1. Carbon Responsibilities Matrix Understanding your progress: This template helps track individual carbon management activities and their associated actions across each project work stage. Shared responsibility: It outlines the responsibilities of each project team memeber for core carbon management activities and assigns individual actions to specific team members. Progress documentation: Use of this type of tracker enables you to document progress and completion of actions at each stage and report this during regular project team meetings.
2. Carbon Opportunities Register Identifying carbon reduction: This template helps the project team identify and assess potential opportunities to reduce the building's carbon footprint. No missed opportunities: By documenting opportunities here, you can ensure that no possible reduction strategy is overlooked or dismissed too quickly. Integration into design: This template allows you to track the process of integrating individual reduction opportunities into the final design.
3. Carbon Management Plan Clear communication: This section outlines the structure and contents required to setup a project speicfic carbon management plan. The plan is intended to act as a framework for communicating progress and desisions made for key carbon focus areas to all project stakeholders at the beginning and end of each work stage. Transparency and clarity: The dissemination of information recorded on the template ensures everyone involved understands the project's carbon management goals and progress across the project’s entire life cycle.
Feedback: Please provide comments and feedback to these templates via the feedback form provided on the Minoro platform page.
Select you project's location to change the region displayed in the action tracker template
| Project Country: | Global

## Carbon Responsibility Matrix
Carbon Responsibilities Matrix
Key Actions |  | Responsibility Matrix | [10 empty] | Action Owner | Status % | Due date | Progress Notes
|  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Client / Owner | Project Manager | Cost Manager | Carbon Manager | Architect | Structural Engineer | Services Engineer | LCA Specialist | Façade Engineer | Main Contractor | Building Manager
|  | Roles: |  | L = Lead |  |  |  | S = Support
5
Stage 0 [Pre-design] - APM 0 [Strategy]
0.01 | Establish Carbon Management Scope | L | S | S | S | - | - | - | - | - | - | - | Owner@Minoro.com | 0 | 2024-01-01 | Update and reissue
0.02 | Challenge the project premise/need | L | S | S | S | - | - | - | - | - | - | S |  | 100
0.03 | Undertake carbon target benchmarking | L | S | S | S | - | - | - | - | - | - | S |  | 50
0.04 | Establish policy & legislative drivers | L | S | S | S | - | - | - | - | - | - | S |  | 60
0.05 | Explore sustainable finance options | L | - | S | - | - | - | - | - | - | - | - |  | 30
0.06 | Explore carbon targets | L | S | S | S | - | - | - | - | - | - | - |  | 20
0.07 | Create carbon management plan | L | S | S | L | - | - | - | - | - | - | S |  | 10
Stage 1 [Pre-design] - APM 1 [Outcome Definition]
1.01 | Adopt measurement standards | S | - | - | L | S | S | S | L | S | - | - |  | -
1.02 | Identify specialist appointments | S | L | S | S | S | S | S | S | - | - | - |  | -
1.03 | Establish energy use intensity targets | S | S | S | L | - | - | L | - | - | - | - |  | -
1.04 | Establish embodied carbon targets | - | - | L | - | S | S | S | L | S | - | - |  | -
1.05 | Identify reduction opportunities | - | - | L | - | S | S | S | L | S | - | - |  | -
1.06 | Update carbon management plan | S | S | S | L | S | S | S | S | S | - | - |  | -
Stage 2 [Design] - APM 2 [Feasibility]
2.01 | Confirm energy use intensity targets | S | S | - | L | S | - | S | - | S | - | S |  | -
2.02 | Evaluate environmental strategies & systems | S | S | S | S | S | - | L | - | S | - | - |  | -
2.03 | Commission energy demand response study | S | S | - | - | - | - | L | - | - | - | - |  | -
2.04 | Setup an operational energy model [B6] | - | - | - | - | S | - | L | - | S | - | - |  | -
2.05 | Identify energy use hotspots | - | - | - | - | S | - | L | - | S | - | - |  | -
2.06 | Establish commissioning framework | S | S | S | - | - | - | L | - | S | - | - |  | -
2.07 | Confirm embodied carbon targets | S | S | S | L | S | - | S | L | S | - | - |  | -
2.08 | Evaluate systems, components & materials | - | - | - | - | L | L | L | S | L | - | - |  | -
2.09 | Setup embodied carbon model [A1-5] | - | - | - | - | S | S | S | L | S | - | - |  | -
2.1 | Identify embodied carbon hotspots | - | - | - | - | S | S | S | L | S | - | - |  | -
2.11 | Setup whole life carbon assessment [A-C] | - | - | - | - | S | S | S | L | S | - | - |  | -
2.12 | Update reduction opportunities | - | S | S | L | S | S | S | - | S | - | - |  | -
2.14 | Update carbon management plan | - | S | S | L | S | S | S | - | S | - | - |  | -
Stage 3 [Design] - APM 3 [Concept Design]
3.01 | Review carbon reduction targets | - | - | - | L | S | S | S | L | S | - | - |  | -
3.02 | Refine environmental strategies & systems | - | - | - | - | S | - | L | - | S | - | - |  | -
3.03 | Mitigate impacts of extreme weather | - | - | - | - | S | S | L | - | S | - | - |  | -
3.04 | Update operational energy model [B6] | - | - | - | - | S | - | L | - | S | - | - |  | -
3.05 | Update energy use hotspots | - | - | - | - | S | - | L | - | S | - | - |  | -
3.06 | Refine systems, components & materials | - | - | - | - | L | L | L | S | L | - | - |  | -
3.07 | Update embodied carbon model [A1-5] | - | - | - | - | S | S | S | L | S | - | - |  | -
3.08 | Update embodied carbon hotspots | - | - | - | - | S | S | - | L | S | - | - |  | -
3.09 | Update whole-life carbon assessment [A-C] | - | - | - | - | S | S | - | L | S | - | - |  | -
3.1 | Update reduction opportunities | - | - | S | L | S | S | S | S | S | - | - |  | -
3.11 | Update carbon management plan | - | S | S | L | S | S | S | S | S | - | - |  | -
3.12 | Engage potential contractors | - | L | - | S | S | S | S | S | S | - | - |  | -
3.13 | Engauge supply-chain | - | - | - | S | L | L | L | L | L | - | - |  | -
3.14 | Finalise tender documentation | - | L | L | S | - | - | - | S | - | - | - |  | -
Stage 4 [Design] - APM 4 [Detailed Design]
4.01 | Finalise contractor scope & responsibilities | - | L | - | S | - | - | - | S | - | S | - |  | -
4.02 | Finalise monitoring, reporting procedures | - | L | - | S | - | - | - | S | - | S | - |  | -
4.03 | Finalise testing & commissioning procedures | - | L | - | - | - | - | S | - | - | S | S |  | -
4.04 | Review carbon reduction targets | - | - | - | L | - | - | - | S | - | S | - |  | -
4.05 | Finalise environmental strategies & systems | - | - | - | - | S | - | L | - | S | S | - |  | -
4.06 | Update operational energy model [B6] | - | - | - | - | S | - | L | - | S | S | - |  | -
4.07 | Finalise systems, components & material | - | - | - | - | L | L | L | S | L | S | - |  | -
4.08 | Update embodied carbon model [A1-5] | - | - | - | - | S | S | S | L | S | S | - |  | -
4.09 | Update whole-life carbon assessment [A-C] | - | - | - | - | S | S | - | L | S | S | - |  | -
4.1 | Update reduction opportunities | - | - | S | L | S | S | S | S | S | S | -
4.11 | Update carbon management plan | - | S | S | L | S | S | S | S | S | S | - |  | -
Stage 5 [Construct] - APM 5 [Delivery]
5.01 | Engage with specialist sub-contractors | - | - | - | S | S | S | S | S | S | L | - |  | -
5.02 | Finalise specialist sub-contractor proposals | - | S | S | S | S | S | S | S | S | L | - |  | -
5.03 | Undertake benchmark testing | - | - | - | - | - | - | S | - | S | L | S |  | -
5.04 | Undertake commissioning | - | - | - | - | - | - | S | - | - | L | S |  | -
5.05 | Update operational energy model [B6] | - | - | - | - | S | - | L | - | S | S | - |  | -
5.06 | Update embodied carbon model [A1-A5] | - | - | - | - | S | S | S | L | S | S | - |  | -
5.07 | Update whole-life carbon assessment [A-C] | - | - | - | - | S | S | - | L | S | S | - |  | -
5.08 | Update reduction opportunities | - | - | S | L | S | S | S | S | S | S | - |  | -
5.09 | Update carbon management plan | - | S | S | L | S | S | S | S | S | S | - |  | -
Stage 6 [Handover] - APM 6 [Project Close]
6.01 | Undertake commissioning handover audit | - | - | - | - | - | - | L | - | - | S | S |  | -
6.02 | Finalise operational energy model [B6] | - | - | - | - | S | - | L | - | S | S | - |  | -
6.03 | Finalise embodied carbon model [A1-A5 | - | - | - | - | S | S | S | L | S | S | - |  | -
6.04 | Finalise whole-life carbon assessment [A-C] | - | - | - | - | S | S | - | L | S | S | - |  | -
6.05 | Update reduction opportunities | - | - | S | L | S | S | S | S | S | S | - |  | -
6.06 | Update carbon management plan | - | S | S | L | S | S | S | S | S | S | - |  | -
Stage 7 [In Use] - APM 7 [Benefits Realisation]
7.01 | Calibrate energy supply & demand | L | - | - | - | - | - | S | - | - | S | L |  | -
7.02 | Update reduction opportunities | S | - | - | L | - | - | - | - | - | - | L |  | -
7.03 | Update carbon management plan | S | - | - | L | - | - | - | - | - | S | L |  | -
Stage 8 [End of life] - APM 7 [Benefits Realisation]
8.01 | Explore life extension opportunities | [12 empty] | - | bar: Responsibility Matrix 8 to Responsibility Matrix 18
Note on Q3: ====== ID#AAABQH0EOpk tc={25CDE3EA-A92F-41A5-A002-592B1A023B8D} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Add due date column
Note on C9: ====== ID#AAABQH0EOpw tc={FFC089A1-C71F-49E4-B0A8-0BC591C75DDC} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Please update to reflect latest actions
Note on D9: ====== ID#AAABQH0EOpc tc={8A5D9403-C9FF-468D-8A8B-0C55AA266479} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Add key to explain Reply: agree - what does L and S mean?
Note on D10: ====== ID#AAABQH0EOpg tc={170A756E-26E0-447F-8E70-12F65DC563D1} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Add key to explain Reply: agree - what does L and S mean?
Note on D11: ====== ID#AAABQH0EOpY tc={1A5537A0-CE68-4037-9EAA-89025492CB05} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Add key to explain Reply: agree - what does L and S mean?
Note on C23: ====== ID#AAABQH0EOpo tc={C0B425E3-673D-441D-BA13-EFB9FB2962DF} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: delete [EDR]

## Carbon Opportunities Register
Carbon Opportunities Register
ID | Building Area / Element | Opportunity Description | Potential Impacts |  |  |  |  | Associated Risks | Mitigation Measures | Follow Up Actions | Owner[s] | Due Date | Status
|  |  | Embodied Carbon | Operational Energy | Programme | Capital Cost | Life Cycle Cost

## Carbon Management Plan
Carbon Management Plan
Maintaining a carbon management plan will ensure that key decisions related to carbon management are being documented, carbon reduction opportunities are being identified and followed up and progress against the agreed carbon reduction targets is being recorded and reported to the relevant project stakeholders. The following
1. Introduction
This section sets out the project outline and ambitions. This should include a brief overview of the project, a statement of whole-life carbon (WLC) frameworks to be used and third party certifications sought as well as target carbon reduction. Sub-headings include: 1.1 Project description 1.2 Project goals: targets & recommendations 1.3 Carbon aspirations: client declaration
2. NZC Activity & Responsibilities
This section sets out the general pathway required to achieve a net zero carbon building and the responsibilities of project team members. Subheadings include: 2.1 Decarbonisation pathway
3. Whole Life Carbon Assessment (WLCA)
This section details the project NZC analysis, benchmarking and findings as well as the carbon reduction strategies. Subheadings include: 3.1 WCLA Methodology 3.2 WCLA Scope 3.3 Annual operational energy/carbon assessment 3.3.1 Baseline operational carbon model 3.3.2 Stage specific operational carbon model 3.3.3 Comparative performance benchmarking 3.3.4 Operational energy / carbon reduction strategies 3.4 Upfront embodied carbon analysis 3.4.1 Baseline upfront embodied carbon model 3.4.2 Embodied carbon reduction strategies 3.4.3 Stage specific upfront embodied carbon model 3.4.4 Comparative performance benchmarking 3.5 Integrated carbon model summary 3.5.1 Comparative performance benchmarking 3.5.2 Lifecycle cost modelling
4. Carbon Offsetting
This section details the method for offsetting the operational and embodied carbon identified in section 3. Subheadings include: 4.1 Carbon offsetting operational energy with on/off site renewables 4.2 Offsetting upfront embodied carbon 4.3 Offsetting costs
5. Third Party Certification
Any targeted third party certifications should be outlined in this section. Subheadings include: 5.1 Third party certification
6. Next Steps
Tasks for future project work stages should be outlined in this section. See decarbonisation pathway for scope of future stages. Subheadings include project stages remaining. These can be: 6.1 Stage 3 - WLC close-out activities 6.1.1 Whole life costing 6.1.2 Client sign off 6.2 Stage 4 - Whole life costing 6.2.1 Continued project whole life carbon/cost analysis 6.2.2 WLC contact specifications
7. Appendix
An appendix should be compiled for tracking of project WLC responsibilities, data modelling, analysis and results.

## Work Stages (Hidden) (hidden)
Regions Pathway Mapping
Global | Europe | UK [RIBA] | UK [PAS 2080] | France | Italy | Spain | USA | Canada | NZ (Aotearoa) | Australia
APM | ACE | RIBA Plan of Works 2020 | PAS 2080 | Ordre des Architectes | Codice appalti (D.Lgs 36/2023) | COAM | AIA | RAIC | NZCIC | NATSPEC
Stage 0 [Pre-design] - APM 0 [Strategy] | Stage 0 [Pre-design] - ACE 0 [Strategy] | Stage 0 [Pre-design] - RIBA 0 [Strategic Definition] | Stage 0 [Pre-design] - PAS 2080 [Need] | Stage 0 [Pre-design] - ODA [AOD] | Stage 0 [Pre-design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 0 [Pre-design] - COAM [Estudios Previos] | Stage 0 [Pre-design] - AIA [Pre-design] | Stage 0 [Pre-design] - RAIC [Not referenced] | Stage 0 [Pre-design] - NZCIC [Pre Design] | Stage 0 [Pre-design] - NATSPEC [Establishment]
Stage 1 [Pre-design] - APM 1 [Outcome Definition] | Stage 1 [Pre-design] - ACE 1 [Initiation] | Stage 1 [Pre-design] - RIBA 1 [Preparation & Briefing] | Stage 1 [Pre-design] - PAS 2080 [Need] | Stage 1 [Pre-design] - ODA [PRE/ESQ] | Stage 1 [Pre-design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 1 [Pre-design] - COAM [Estudios Previos] | Stage 1 [Pre-design] - AIA [Pre-design] | Stage 1 [Pre-design] - RAIC [Pre Design] | Stage 1 [Pre-design] - NZCIC [Pre Design] | Stage 1 [Pre-design] - NATSPEC [Establishment]
Stage 2 [Design] - APM 2 [Feasibility] | Stage 2 [Design] - ACE 2.1 & 2.2 [Concept & Preliminary Design] | Stage 2 [Design] - RIBA 2 [Concept Design] | Stage 2 [Design] - PAS 2080 [Optioneering] | Stage 2 [Design] - ODA [APS] | Stage 2 [Design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 2 [Design] - COAM [Proyecto Básico] | Stage 2 [Design] - AIA [Schematic Design] | Stage 2 [Design] - RAIC [Schematic Design] | Stage 2 [Design] - NZCIC [Concept & Preliminary Design] | Stage 2 [Design] - NATSPEC [Concept Design & Schematic Design]
Stage 3 [Design] - APM 3 [Concept Design] | Stage 3 [Design] - ACE 2.3 [Developed Design] | Stage 3 [Design] - RIBA 3 [Schematic Design] | Stage 3 [Design] - PAS 2080 [Design] | Stage 3 [Design] - ODA [ADP & DPC] | Stage 3 [Design] - Codice appalti (D.Lgs 36/2023) [PFTE] | Stage 3 [Design] - COAM [Proyecto Básico] | Stage 3 [Design] - AIA [Design Development] | Stage 3 [Design] - RAIC [Construction Documents] | Stage 3 [Design] - NZCIC [Developed Design] | Stage 3 [Design] - NATSPEC [Design Development]
Stage 4 [Design] - APM 4 [Detailed Design] | Stage 4 [Design] - ACE 2.4 [Detailed Design] | Stage 4 [Design] - RIBA 4 [Technical Design] | Stage 4 [Design] - PAS 2080 [Design] | Stage 4 [Design] - ODA [PRO & DCE] | Stage 4 [Design] - Codice appalti (D.Lgs 36/2023) [Progetto Esecutivo] | Stage 4 [Design] - COAM [Proyecto de Ejecución] | Stage 4 [Design] - AIA [Construction Documents] | Stage 4 [Design] - RAIC [Construction Procurement] | Stage 4 [Design] - NZCIC [Detailed Design] | Stage 4 [Design] - NATSPEC [Contract Documentation]
Stage 5 [Construct] - APM 5 [Delivery] | Stage 5 [Construct] - ACE 3 [Construction] | Stage 5 [Construct] - RIBA 5 [Manufacture & Construction] | Stage 5 [Construct] - PAS 2080 [Delivery] | Stage 5 [Construct] - ODA [MDT, VISA & DET] | Stage 5 [Construct] - Codice appalti (D.Lgs 36/2023) [Esecuzione Iavori] | Stage 5 [Construct] - COAM [Dirección de Obra] | Stage 5 [Construct] - AIA [Construction Administration] | Stage 5 [Construct] - RAIC [Construction Contract Administration and Field Review] | Stage 5 [Construct] - NZCIC [Construction] | Stage 5 [Construct] - NATSPEC [Construction]
Stage 6 [Handover] - APM 6 [Project Close] | Stage 6 [Handover] - ACE [Not referenced] | Stage 6 [Handover] - RIBA 6 [Handover] | Stage 6 [Handover] - PAS 2080 [Delivery] | Stage 6 [Handover] - ODA [AOR & DOE] | Stage 6 [Handover] - Codice appalti (D.Lgs 36/2023) [Collaudo & Conclusione] | Stage 6 [Handover] - COAM [Liquidación y Recepción] | Stage 6 [Handover] - AIA [Construction Administration] | Stage 6 [Handover] - RAIC [Take-over Procedures, Comissioning and Post-occupancy Evaluation] | Stage 6 [Handover] - NZCIC [Not referenced] | Stage 6 [Handover] - [Not referenced]
Stage 7 [In Use] - APM 7 [Benefits Realisation] | Stage 7 [In Use] - ACE 4 [Building Use] | Stage 7 [In Use] - RIBA 7 [Use] | Stage 7 [In Use] - PAS 2080 [Operation] | Stage 7 [In Use] - ODA [Exploitation du bâtiment] | Stage 7 [In Use] - Codice appalti (D.Lgs 36/2023) [Funzionalita] | Stage 7 [In Use] - COAM [Liquidación y Recepción] | Stage 7 [In Use] - AIA [Not referenced] | Stage 7 [In Use] - RAIC [Take-over Procedures, Comissioning and Post-occupancy Evaluation] | Stage 7 [In Use] - NZCIC [Operate] | Stage 7 [In Use] - NATSPEC [Operate]
Stage 8 [End of life] - APM 7 [Benefits Realisation] | Stage 8 [End of life] - ACE 5 [End of Life] | Stage 8 [End of life] - RIBA [Not referenced] | Stage 8 [End of life] - PAS 2080 [Purppose/ Performance Review] | Stage 8 [End of life] - ODA [Fin di vie] | Stage 8 [End of life] - Codice appalti (D.Lgs 36/2023) [Dismissione] | Stage 8 [End of life] - COAM [Not referenced] | Stage 8 [End of life] - AIA [Not referenced] | Stage 8 [End of life] - RAIC [Not referenced] | Stage 8 [End of life] - NZCIC [Not referenced] | Stage 8 [End of life] - NATSPEC [Not Referenced]
Note on B2: ====== ID#AAABQH0EOps tc={5DE7730C-CEED-450F-97DD-3CF7F7D71C23} (2024-06-20 13:07:04) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Steven Smith - Please lockdown and hide this tab